## Sprint 1
ITSC-3155 Software Engineering
Sprint Backlog NOV 17 - 21
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Menu Management | 8 |  | 9 | 2 | 3 | 2 | 2 | 2 | 2 | To Do
S1-T1 POST /menu-items | 8 | Team | 3 | 1 | 2 | 1 | 1 | 1 | 1 | Done | 1
S1-T2 GET /menu-items | 8 | Team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
S1-T3 PUT /menu-items | 8 | Team | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 1
S1-T4 DELETE /menu-items | 8 | Team | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 1
Customer Management | 13 |  | 8 | 2 | 2 | 2 | 1 | 1 | 0 | To Do
S1-T5 POST /customers | 13 | Team | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 1
S1-T6 GET /customers | 13 | Team | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | 1
S1-T7 PUT/DELETE customers | 13 | Team | 3 | 1 | 0 | 0 | 1 | 1 | 0 | Done | 1
Order Management | 8 |  | 12 | 3 | 2 | 2 | 2 | 2 | 1 | To Do
S1-T8 POST /orders | 8 | Team | 4 | 2 | 1 | 1 | 0 | 0 | 0 | Done | 1
S1-T9 GET /orders | 8 | Team | 3 | 1 | 0 | 1 | 1 | 0 | 0 | Done | 1
S1-T10 POST /order-details | 8 | Team | 3 | 0 | 1 | 0 | 1 | 1 | 0 | Done | 1
S1-T11 GET /order-details | 8 | Team | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 1
API Development | 8 |  | 10 | 2 | 3 | 2 | 0 | 0 | 0 | To Do
S1-T12 Project Structure | 8 | Team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
S1-T13 Swagger Setup | 8 | Team | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Done | 1
S1-T14 POST /sandwiches | 8 | Team | 2 | 1 | 0 | 1 | 0 | 0 | 0 | Done | 1
S1-T15 GET /sandwiches | 8 | Team | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | 1
S1-T16 PUT/DELETE sandwiches | 8 | Team | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done | 1
Database Integration | 5 |  | 5 | 1 | 1 | 1 | 2 | 0 | 0 | To Do
S1-T17 Verify Models | 5 | Team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
S1-T18 DB Session CRUD | 5 | Team | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 1
S1-T19 Seed Sample Data | 5 | Team | 1 | 0 | 0 | 0 | 1 | 0 | 0 | Done | 1
TOTAL |  |  | 88 | 20 | 11 | 19 | 15 | 11 | 6 |  | 19

## Sprint 2
ITSC-3155 Software Engineering
Sprint Backlog Nov 24 - 28
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
Menu Management | 5 | Team | 4 | 1 | 1 | 1 | 1 | 1 | 0 | Done
S2-T1 Add promotion_id support to menu-items | 5 | Team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
S2-T2 Add average rating to menu-item GET response | 5 | Team | 2 | 0 | 0 | 1 | 1 | 1 | 0 | Done | 1
Order Placement | 13 | Team | 10 | 2 | 2 | 3 | 3 | 2 | 0 | Done | 2
S2-T3 Add payments CRUD endpoints | 13 | Team | 4 | 2 | 1 | 1 | 0 | 0 | 0 | Done | 1
S2-T4 Integrate payments into order creation | 13 | Team | 2 | 0 | 1 | 1 | 1 | 1 | 0 | Done | 1
S2-T5 Apply promotion discount to order total | 13 | Team | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 1
S2-T6 Add final price calculation | 13 | Team | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 1
Order Management Dashboard | 5 | Team | 10 | 2 | 4 | 5 | 5 | 2 | 0 | Done | 4
S2-T7 Add order status update endpoint | 5 | Team | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 1
S2-T8 Add date filter to GET /orders | 5 | Team | 2 | 1 | 3 | 3 | 3 | 0 | 0 | Done | 1
S2-T9 Add sorting (price/date) to orders | 5 | Team | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 1
S2-T10 Add order summary fields (item count, discount, totals) | 5 | Team | 3 | 0 | 0 | 0 | 1 | 2 | 0 | Done | 1
API Development / CRUD | 13 | Team | 14 | 3 | 3 | 4 | 3 | 1 | 0 | Done | 4
S2-T11 Add promotions CRUD | 13 | Team | 4 | 2 | 1 | 1 | 0 | 0 | 0 | Done | 1
S2-T12 Add reviews CRUD | 13 | Team | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 1
S2-T13 Add validation for all request bodies | 13 | Team | 3 | 0 | 1 | 1 | 1 | 0 | 0 | Done | 1
S2-T14 Add missing DELETE endpoints | 13 | Team | 3 | 0 | 0 | 1 | 1 | 1 | 0 | Done | 1
Database Integration | 8 | Team | 8 | 2 | 2 | 2 | 1 | 1 | 0 | Done | 4
S2-T15 Add DB indexes for performance | 8 | Team | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
S2-T16 Add join relationships (orders ↔ order_details) | 8 | Team | 3 | 1 | 0 | 1 | 1 | 0 | 0 | Done | 1
S2-T17 Final DB validation + seed refresh | 8 | Team | 3 | 0 | 1 | 1 | 0 | 1 | 0 | Done | 1
TOTAL |  |  | 46 | 10 | 12 | 15 | 13 | 7 | 0 |  | 14