## Sheet3
Task | Priority | Status | Due Date | Notes
Github Repo Creation | High | In progress | 2025-10-24 | Create a new clean repository. Invite your group member as well as Instructor team, Professor and TAs. Download the code skeleton and push it to the repository with a proper commit message. The rest of the group should clone the project using git clone <repo_address>. NOT USER STORY
Project Setup | High | Not started | 2025-10-24 | Create a Virtual Environment and install dependencies. Run the FastApi server and test the sample code. NOT USER STORY
Requirement Analysis and User Stories | High | In progress | 2025-10-24 | Pay close attention to what the client wants. Extract requirements and fill out a product backlog. Create User Stories for your backlogs. NOT USER STORY
Menu Management | High | Not started | 2025-12-02 | Staff can create, edit, or delete menu items (name, price, ingredients, categorty). USER STORY
Order Placement | High | Not started | 2025-12-02 | Customers place orders as guests (name, phone, address) and select meals. USER STORY
Order Management Dashboard | High | Not started | 2025-12-02 | Staff views all orders, filter by date/status, and update order progress. USER STORY
API Development | High | Not started | 2025-12-02 | Developers build CRUD API endpoints for menus, orders, reviews, and promos. Ensures all endpoints function properly in Swagger UI. USER STORY
Database integration | High | Not started | 2025-12-02 | Developers connect API routes to MySQL database tables (menu, orders, reviews, promos). Verify all CRUD operations work correctly. USER STORY
Payment Processing | High | Not started | 2025-12-02 | Support multiple payment methods (card, cash on delivery). Lets customers pay securely using different payment options. USER STORY
Input validation | Medium | Not started | 2025-12-02 | Developers implement form and data validation to prevent missing or incorrect inputs. USER STORY
Order Tracking | Medium | Not started | 2025-12-02 | Customers track order status with tracking number (preparing, out for delivery, delivered). USER STORY
Promotions / Discount Codes | Medum | Not started | 2025-12-02 | Staff create promo codes with expiration dates and discounts amounts. USER STORY
Customer Reviews | Medium | Not started | 2025-12-02 | Customers leave ratings and comments about their order. USER STORY
Error handling and logging | Medium | Not started | 2025-12-02 | Developers add error messages and logging to monitor system performance and identify bugs. USER STORY
Reports and Analytics | Low | Not started | 2025-12-02 | Owner views sales totals, popular meals, and custimer trends. USER STORY
Code Documentation | Low | Not started | 2025-12-02 | Developers write clear code comments and endpoint documentation for maintainablility. USER STORY
Authentication (This could also be an optional add) | Low | Not started | 2025-12-02 | Optional staff login for menu and order management access.USER STORY
Documentation and Setup | Low | Not started | 2025-12-02 | Provide setup instructions and system training materials. USER STORY